## owssvr
Title | LSAIB Revision | Product Number | CI/CSCI | As-Delivered NHA | Product Title | Product Revision | Link | CR Number | Directive Status | Review Status | Approving Directive | GSDO OPE | Sensitivity | Change Type | Change | Change Driver | Program/Element | OTRR Milestone | Item Status | Reference Information | Doc Type | Verification | IPCA CI ID | Audit ID | Created | Created By | Modified | Modified By | Board Date | Item Type | Path
Standard For Booster Configuration, Space Launch System | Baseline | STW9-19166 | 97M62060-001 |  | Standard For Booster Configuration, Space Launch System | A | Link to Product | GSDO-C0783-X Rev A | Approved | Approved | GSDO-D0783-X R1 | Jones, John T. | ITAR | CR | Superceded | Booster Request | SLS/Booster | Aft Booster Assembly Buildup | Baselined | ​This Spec was superseded by STW9-19166, Rev B | Spec | VR | CI-1E - Solid Rocket Booster (SRB) |  | 2016-12-12 10:27 | Paule, Lori A. (KSC-LXB30) | 2018-10-31 15:17 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 04/04/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Battery Installation, CBC/DCSS, Launch Site | A | 1G25675 | 1G50001 | 1G50000 | Battery Installation, CBC/DCSS, Launch Site | C | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0888-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Superceded | ICPS Request | SLS/SPIE |  | Baselined | ​Reference Loose Items Kit 1G50141 |  | VR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-10-16 13:45 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:19 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Propulsion Instl, Field Site, ICPS - VAB | A | 1G50042 | 1G50001 | 1G50000 | Propulsion Instl, Field Site, ICPS - VAB | - | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0888-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | ICPS Request | SLS/SPIE |  | Baselined | ​Reference Loose Items Kit 1G50141 | Drawing | VR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-10-17 09:14 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:19 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Secondary Structures Instl, Second Stage, ICPS 5M | A | 1G50101 | 1G50001 | 1G50000 | Secondary Structures Instl, Second Stage, ICPS 5M | D | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0888-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | ICPS Request | SLS/SPIE |  | Baselined | ​Reference Loose Items Kit 1G50141 | Drawing | NVR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-10-17 09:21 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:27 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Field Site Instl, Second Stage, ICPS 5M | A | 1G50138 | 1G50001 | 1G50000 | Field Site Instl, Second Stage, ICPS 5M | A | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0888-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | ICPS Request | SLS/SPIE |  | Baselined | ​Reference Loose Items Kit 1G50141 | Drawing | NVR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-10-17 09:24 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:26 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Bracket Installation, Aft Reflectors, ICPS | A | 1G50139 | 1G50001 | 1G50000 | Bracket Installation, Aft Reflectors, ICPS | - | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0888-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | ICPS Request | SLS/SPIE |  | Baselined | ​Reference Loose Items Kit 1G50141 | Drawing | VR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-10-17 09:26 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:19 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Blanket Instl, Hydrazine Bottle, Launch Site-ICPS | A | 1G50144 | 1G50001 | 1G50000 | Blanket Instl, Hydrazine Bottle, Launch Site-ICPS | A | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0888-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Superceded | ICPS Request | SLS/SPIE |  | Baselined | ​Reference Loose Items Kit 1G50141 |  | VR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-10-17 09:28 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:19 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Blanket Instl, Equipment Shelf, Launch Site - ICPS | A | 1G50145 | 1G50001 | 1G50000 | Blanket Instl, Equipment Shelf, Launch Site - ICPS | B | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0889 | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Superceded | ICPS Request | SLS/SPIE |  | Baselined | ​Reference Loose Items Kit 1G50141 |  | VR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-10-17 09:48 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:19 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Design Standard Requirements for Critical Design Characteristics | A | 0-70924 | 1G50001 | 1G50000 | Design Standard Requirements for Critical Design Characteristics | C | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0888-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Superceded | ICPS Request | SLS/SPIE |  | Baselined |  |  | VR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-10-17 09:50 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:19 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Cleanliness for Fuel and Oxidizer Systems and Related Pneumatic Systems | A | 1P00071 | 1G50001 | 1G50000 | Cleanliness for Fuel and Oxidizer Systems and Related Pneumatic Systems | P | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0888-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | ICPS Request | SLS/SPIE |  | Baselined |  | Spec | NVR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-10-17 09:53 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:19 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Process Specification, Tubing, Fittings and Coupling Nuts, Installation of | A | 1P00080 | 1G50001 | 1G50000 | Process Specification, Tubing, Fittings and Coupling Nuts, Installation of | L | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0888-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | ICPS Request | SLS/SPIE |  | Baselined |  | Spec | NVR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-10-17 09:56 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:19 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Methods, Marking | A | STD0108 | 1G50001 | 1G50000 | Methods, Marking | F | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0888-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | ICPS Request | SLS/SPIE |  | Baselined |  | Spec | NVR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-10-17 10:17 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-11-01 09:24 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Bonding, Electrical, Surface Preparation For | A | STP0084 | 1G50001 | 1G50000 | Bonding, Electrical, Surface Preparation For | C | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0888-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | ICPS Request | SLS/SPIE |  | Baselined |  | Spec | NVR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-10-17 10:23 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-11-01 09:24 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Lubricants, Application, Threaded Surfaces, O-Rings and Seals | A | STP0131 | 1G50001 | 1G50000 | Lubricants, Application, Threaded Surfaces, O-Rings and Seals | E | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0888-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | ICPS Request | SLS/SPIE |  | Baselined |  | Spec | NVR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-10-17 10:35 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-11-01 09:24 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Process Specification, Sealing Process, For | A | STP0150 | 1G50001 | 1G50000 | Process Specification, Sealing Process, For | E | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0888-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | ICPS Request | SLS/SPIE |  | Baselined |  | Spec | NVR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-10-17 10:37 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-11-01 09:24 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Process Specification, Bonding and Sealing, Surface Preparation For | A | STP0151 | 1G50001 | 1G50000 | Process Specification, Bonding and Sealing, Surface Preparation For | T | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0888-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | ICPS Request | SLS/SPIE |  | Baselined |  | Spec | NVR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-10-17 10:46 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-11-01 09:24 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Bolts, Screws, Nuts, Nutplates, and Washers, Installation and Inspection of | A | STP0381 | 1G50001 | 1G50000 | Bolts, Screws, Nuts, Nutplates, and Washers, Installation and Inspection of | V | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0888-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Superceded | ICPS Request | SLS/SPIE |  | Baselined | ​STP0381 was superseded by STP1023 per GSDO-C1048-X |  | VR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-10-17 11:04 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-11-01 09:24 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Cleanliness of Aerospace Hardware, Maintenance of | A | STP0413 | 1G50001 | 1G50000 | Cleanliness of Aerospace Hardware, Maintenance of | G | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0888-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | ICPS Request | SLS/SPIE |  | Baselined |  | Spec | NVR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-10-17 11:07 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-11-01 09:24 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Electronic Parts and Equipment, Static Sensitive, Protection of | A | STP0468 | 1G50001 | 1G50000 | Electronic Parts and Equipment, Static Sensitive, Protection of | G | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0889 | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | ICPS Request | SLS/SPIE |  | Baselined |  | Spec | NVR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-10-17 11:10 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-11-01 09:24 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Standard, Multilayer Insulation, Contamination Control of | A | STP0503 | 1G50001 | 1G50000 | Standard, Multilayer Insulation, Contamination Control of | A | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0888-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | ICPS Request | SLS/SPIE |  | Baselined |  | Spec | NVR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-10-17 11:14 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-11-01 09:24 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Electrical Equipment Installation, Launch Site | A | 1G25676 | 1G50001 | 1G50000 | Electrical Equipment Installation, Launch Site | A | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0888-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Superceded | ICPS Request | SLS/SPIE |  | Baselined |  |  | VR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-11-21 10:07 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:19 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Installation, Pre-VAB | A | 1G50009 | 1G50001 | 1G50000 | Installation, Pre-VAB | - | Link to SLS Portal | GSDO-C0888-X | Approved | Approved | GSDO-D0888-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Superceded | SLS/SPIE Request | SLS/SPIE |  | Baselined |  |  | VR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2017-11-21 10:12 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:16 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 11/28/2017 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
LVSA Integrated Assembly | B | 18610001 | 97M62215-001 |  | LVSA Integrated Assembly | - | Link to SLS Portal | GSDO-C0912-X | Approved | Approved | GSDO-D0912-X | Bengoa, Alex | ITAR | CR | Superceded | LVSA Request | SLS/SPIE |  | Baselined |  | Drawing | VR | CI-1.b - Launch Vehicle Stage Adapter (LVSA) |  | 2017-11-27 13:43 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-12-06 08:42 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 01/09/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Door, Access Installation - LVSA | B | 18610016 | 97M62215-001 |  | Door, Access Installation - LVSA | A | Link to SLS Portal | GSDO-C0912-X | Approved | Approved | GSDO-D0912-X | Bengoa, Alex | ITAR | CR | Superceded | LVSA Request | SLS/SPIE | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined | ​This item was superceded by [18610026, (Door, Access Installation, Flight LVSA) Rev New] upon approval of GSDO-D1140-X in December 2018. | Drawing | VR | CI-1.b - Launch Vehicle Stage Adapter (LVSA) |  | 2017-11-27 13:47 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-12-06 08:49 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 01/09/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Door Access Kit - LVSA | B | 38610445 | 97M62215-001 |  | Door Access Kit - LVSA | B | Link to SLS Portal | GSDO-C0912-X | Approved | Approved | GSDO-D0912-X | Bengoa, Alex | ITAR | CR | Superceded | LVSA Request | SLS/SPIE |  | Baselined |  |  | VR | CI-1.b - Launch Vehicle Stage Adapter (LVSA) |  | 2017-11-27 13:50 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:20 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 01/09/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Access Cover Instl. | B | 97M62179-001 | 97M62179-001 | 97M62020-001 | Access Cover Instl. | - | Link to SLS Portal | GSDO-C0912-X | Approved | Approved | GSDO-D0912-X | Bengoa, Alex | ITAR | CR | Add | MSA Request | SLS/SPIE |  | Baselined |  | Drawing | VR | CI-1.c - Multi-Purpose Crew Vehicle (MPCV) Stage Adapter (MSA) | 32 - MPCV/Stage Adapter (MSA) Preliminary ADP - - Preliminary / Flight | 2017-11-27 13:53 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:22 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 01/09/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Blanket Installation, Prop Panel, Second Stage | C | 1G15365 | 1G50000 | 1G50000 | Blanket Installation, Prop Panel, Second Stage | - | Link to Product | GSDO-C0947-X | Approved | Approved | GSDO-D0947-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | ICPS Request | SLS/SPIE |  | Baselined |  | Drawing | VR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2018-02-20 16:00 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-03 14:06 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 03/27/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Launch Site Assy - Second Stage | C | 1G50000 | 1G50000 | 1G50000 | Launch Site Assy - Second Stage | E | Link to Product | GSDO-C0947-X | Approved | Approved | GSDO-D0947-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | ICPS Request | SLS/SPIE |  | Baselined |  | Drawing | VR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2018-02-20 16:09 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-03 14:06 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 03/27/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Electrical Equipment Installation, Launch Site | C | 1G51006 | 1G50000 | 1G50000 | Electrical Equipment Installation, Launch Site | B | Link to product | GSDO-C0947-X | Approved | Approved | GSDO-D0947-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | ICPS Request | SLS/SPIE |  | Baselined |  | Drawing | VR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2018-02-20 16:13 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-03 14:06 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 03/27/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Core Stage Attach Ring Kit Assembly |  | 1U122586 | 97M62060-001 |  | Core Stage Attach Ring Kit Assembly | A |  |  | Approved |  | GSDO-IDM-036 | Jones, John T. | ITAR | IDM | Superceded | GSDO IDM | SLS/Booster | Solid Rocket Booster Stacking | Baselined | This IDM has been superceded by CR GSDO-C0996-X, Rev A. |  | VR | CI-1E - Solid Rocket Booster (SRB) |  | 2018-03-08 13:44 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-05-31 09:57 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] |  | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Installation, Stack Integration Facility, EM1 | D | 948YA0000040-501 | 948YA0000000-501 | 97M62030-001 | Installation, Stack Integration Facility, EM1 | - | Link to Product | GSDO-C0996-X Rev A | Approved | Approved | GSDO-D0996-X | Aviles, Kristan | ITAR | CR | Add | Orion Request | MPCV/Orion | Orion Servicing | Baselined |  | Drawing | VR | CI-2A - Integrated Stack Assembly EM-1 (Orion Crew Vehicle) |  | 2018-04-09 14:28 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-06-04 13:36 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 05/29/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Installation, LAS-CM R&R, Stack | D | 948YN0650042-501 | 948YA0000000-501 | 97M62030-001 | Installation, LAS-CM R&R, Stack | - | Link to Product | GSDO-C0996-X Rev A | Approved | Approved | GSDO-D0996-X | Aviles, Kristan | ITAR | CR | Add | Orion Request | MPCV/Orion | Orion Servicing | Baselined |  | Drawing | VR | CI-2A - Integrated Stack Assembly EM-1 (Orion Crew Vehicle) |  | 2018-04-09 14:40 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-05-30 11:45 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 05/29/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
LAS Closeout Kit, Operational | D | 948LA0010033-501 | 948YA0000000-501 | 97M62030-001 | LAS Closeout Kit, Operational | - | Link to Product | GSDO-C0996-X Rev A | Approved | Approved | GSDO-D0996-X | Aviles, Kristan | ITAR | CR | Add | Orion Request | MPCV/Orion | Orion Servicing | Baselined |  | Drawing | VR | CI-2A - Integrated Stack Assembly EM-1 (Orion Crew Vehicle) |  | 2018-04-09 14:46 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-05-30 11:45 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 05/29/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
OGIVE Installation Kit, Operational | D | 948LA0010047-501 | 948YA0000000-501 | 97M62030-001 | OGIVE Installation Kit, Operational | - | Link to Product | GSDO-C0996-X Rev A | Approved | Approved | GSDO-D0996-X | Aviles, Kristan | ITAR | CR | Add | Orion Request | MPCV/Orion | Orion Servicing | Baselined |  | Drawing | VR | CI-2A - Integrated Stack Assembly EM-1 (Orion Crew Vehicle) |  | 2018-04-09 14:50 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-05-30 11:45 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 05/29/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Installation Drawing, Ground, LAS T-0 Umbilical | D | 948MA6042000 | 948YA0000000-501 | 97M62030-001 | Installation Drawing, Ground, LAS T-0 Umbilical | - | Link to Product | GSDO-C0996-X Rev A | Approved | Approved | GSDO-D0996-X | Aviles, Kristan | ITAR | CR | Add | Orion Request | MPCV/Orion | Orion Servicing | Baselined |  | Drawing | VR | CI-2A - Integrated Stack Assembly EM-1 (Orion Crew Vehicle) |  | 2018-04-09 14:55 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-05-30 11:45 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 05/29/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Installation Kit, Thermal Protection | D | 948YN0800040-501 | 948YA0000000-501 | 97M62030-001 | Installation Kit, Thermal Protection | A | Link to Product | GSDO-C0996-X Rev A | Approved | Approved | GSDO-D0996-X | Aviles, Kristan | ITAR | CR | Add | Orion Request | MPCV/Orion | Orion Servicing | Baselined |  | Drawing | VR | CI-2A - Integrated Stack Assembly EM-1 (Orion Crew Vehicle) |  | 2018-04-09 14:58 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-09 11:05 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 05/29/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Kit, Mechanical, Ship Loose | D | 948YN1010041-501 | 948YA0000000-501 | 97M62030-001 | Kit, Mechanical, Ship Loose | - | Link to Product | GSDO-C0996-X Rev A | Approved | Approved | GSDO-D0996-X | Aviles, Kristan | ITAR | CR | Add | Orion Request | MPCV/Orion | Orion Servicing | Baselined |  | Drawing | VR | CI-2A - Integrated Stack Assembly EM-1 (Orion Crew Vehicle) |  | 2018-04-09 15:01 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-05-30 11:45 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 05/29/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Kit, Bulk Items, Ship Loose | D | 948YN1010042-501 | 948YA0000000-501 | 97M62030-001 | Kit, Bulk Items, Ship Loose | - | Link to Product | GSDO-C0996-X Rev A | Approved | Approved | GSDO-D0996-X | Aviles, Kristan | ITAR | CR | Add | Orion Request | MPCV/Orion | Orion Servicing | Baselined |  | Drawing | VR | CI-2A - Integrated Stack Assembly EM-1 (Orion Crew Vehicle) |  | 2018-04-09 15:03 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-05-30 11:45 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 05/29/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Kit, Place Holder, Ship Loose | D | 948YN1010043-501 | 948YA0000000-501 | 97M62030-001 | Kit, Place Holder, Ship Loose | - | Link to Product | GSDO-C0996-X Rev A | Approved | Approved | GSDO-D0996-X | Aviles, Kristan | ITAR | CR | Add | Orion Request | MPCV/Orion | Orion Servicing | Baselined |  | Drawing | VR | CI-2A - Integrated Stack Assembly EM-1 (Orion Crew Vehicle) |  | 2018-04-09 15:05 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-05-30 11:45 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 05/29/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Motor Assembly, LAS, EM-1 | D | 948LA0010046-501 | 948YA0000000-501 | 97M62030-001 | Motor Assembly, LAS, EM-1 | - | link to product | GSDO-C0996-X Rev A | Approved | Approved | GSDO-D0996-X | Aviles, Kristan | ITAR | CR | Add | Orion Request | MPCV/Orion | Orion Servicing | Baselined |  | Drawing | VR | CI-2A - Integrated Stack Assembly EM-1 (Orion Crew Vehicle) |  | 2018-04-30 13:46 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-03 14:54 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 05/29/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Integrated Stack Assembly, Exploration Mission 1 | D | 948YA0000000-501 | 948YA0000000-501 | 97M62030-001 | Integrated Stack Assembly, Exploration Mission 1 | - | Link to Product | GSDO-C0996-X Rev A | Approved | Approved | GSDO-D0996-X | Aviles, Kristan | ITAR | CR | Add | Orion Request | MPCV/Orion | Orion Servicing | Baselined |  | Drawing | VR | CI-2A - Integrated Stack Assembly EM-1 (Orion Crew Vehicle) |  | 2018-04-30 13:58 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-03 14:50 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 05/29/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Kit, Flight Hardware, Ship Loose | D | 948YN1010036-501 | 948YA0000000-501 | 97M62030-001 | Kit, Flight Hardware, Ship Loose | - | Link to Product | GSDO-C0996-X Rev A | Approved | Approved | GSDO-D0996-X | Aviles, Kristan | ITAR | CR | Add | Orion Request | MPCV/Orion | Orion Servicing | Baselined |  | Drawing | VR | CI-2A - Integrated Stack Assembly EM-1 (Orion Crew Vehicle) |  | 2018-04-30 14:03 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-03 15:10 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 05/29/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Kit, Mechanical, Ship Loose | D | 948YN1010037-501 | 948YA0000000-501 | 97M62030-001 | Kit, Mechanical, Ship Loose | - | Link to Product | GSDO-C0996-X Rev A | Approved | Approved | GSDO-D0996-X | Aviles, Kristan | ITAR | CR | Add | Orion Request | MPCV/Orion | Orion Servicing | Baselined |  | Drawing | VR | CI-2A - Integrated Stack Assembly EM-1 (Orion Crew Vehicle) |  | 2018-04-30 14:13 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-03 15:12 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 05/29/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Kit, Flight Fasteners | D | 948YN1010038-501 | 948YA0000000-501 | 97M62030-001 | Kit, Flight Fasteners | - | Link to Product | GSDO-C0996-X Rev A | Approved | Approved | GSDO-D0996-X | Aviles, Kristan | ITAR | CR | Add | Orion Request | MPCV/Orion | Orion Servicing | Baselined |  | Drawing | VR | CI-2A - Integrated Stack Assembly EM-1 (Orion Crew Vehicle) |  | 2018-04-30 14:16 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-03 15:14 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 05/29/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Kit, Bulk Items, Ship Loose | D | 948YN1010039-501 | 948YA0000000-501 | 97M62030-001 | Kit, Bulk Items, Ship Loose | - | Link to Product | GSDO-C0996-X Rev A | Approved | Approved | GSDO-D0996-X | Aviles, Kristan | ITAR | CR | Add | Orion Request | MPCV/Orion | Orion Servicing | Baselined |  | Drawing | VR | CI-2A - Integrated Stack Assembly EM-1 (Orion Crew Vehicle) |  | 2018-04-30 14:19 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-03 15:15 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 05/29/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Standard for Booster Configuration, Space Launch System |  | STW9-19166 | 97M62060-001 | 97M62040-001 | Standard for Booster Configuration, Space Launch System | B | Link to Specification | GSDO-C1020-X | Approved | Approved | GSDO-D1020-X | Jones, John T. | ITAR | CR | Update | Booster Request | SLS/Booster | Aft Booster Assembly Buildup | Baselined | ​This Spec supersedes STW9-19166 Revision A, and also supersedes GSDO-IDM-036. | Spec | VR | CI-1E - Solid Rocket Booster (SRB) |  | 2018-05-14 15:57 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-03 15:55 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 06/12/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Equipment List, Protective Devices - Engine, Core Stage |  | RK395-00021A1 | 97M62040-001 | 97M62040-001 | Equipment List, Protective Devices - Engine, Core Stage | B | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Drawing | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 12:22 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Equipment List, Protective Devices |  | RK395-00021A1.DRW Notes | 97M62040-001 | 97M62040-001 | Equipment List, Protective Devices | 2 | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Drawing | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 12:41 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
PROTECTIVE DEVICES: USAGE, HANDLING, STORAGE, MAINTENANCE, AND INSPECTION OF | - | RK0616-0019 | 97M62040-001 | 97M62040-001 | PROTECTIVE DEVICES: USAGE, HANDLING, STORAGE, MAINTENANCE, AND INSPECTION OF | A | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Spec | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:28 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
PROT DEV INSTL - DFI | - | RK395-00023A1 | 97M62040-001 | 97M62040-001 | PROT DEV INSTL - DFI | A | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Drawing | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
PROTECTIVE DEVICES, INSTALLATION, ROCKET ENGINE | - | RK395-00150 | 97M62040-001 | 97M62040-001 | PROTECTIVE DEVICES, INSTALLATION, ROCKET ENGINE | AH | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Drawing | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
PROTECTIVE DEVICES - ROCKET ENGINE, Revision Record | - | RR-RK395-00150-AG | 97M62040-001 | 97M62040-001 | PROTECTIVE DEVICES - ROCKET ENGINE, Revision Record | New | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Drawing | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-11-01 09:24 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Task Attachment on RK395-00150, Rev AG | - | UC-018643 | 97M62040-001 | 97M62040-001 | Task Attachment on RK395-00150, Rev AG | New | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined | ​EO to RK395-00150 | EO | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Task Attachment on RK395-00150, Rev AG | - | UC-018244 | 97M62040-001 | 97M62040-001 | Task Attachment on RK395-00150, Rev AG | New | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined | ​EO to RK395-00150 | EO | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Task Attachment on RK395-00150, Rev AG | - | UC-010766 | 97M62040-001 | 97M62040-001 | Task Attachment on RK395-00150, Rev AG | New | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined | ​EO to RK395-00150 | EO | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
INSTALLING AND REMOVING SSME FERRY FLIGHT SET | - | RF0004-431 | 97M62040-001 | 97M62040-001 | INSTALLING AND REMOVING SSME FERRY FLIGHT SET | D | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Spec | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
PROT DEV INSTL - FEED LINE | - | RK395-00026A1 | 97M62040-001 | 97M62040-001 | PROT DEV INSTL - FEED LINE | A | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Drawing | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
RS-25 ENGINE INSPECTION CRITERIA | - | RF0001-053 | 97M62040-001 | 97M62040-001 | RS-25 ENGINE INSPECTION CRITERIA | AN | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Spec | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
ENGINE ASSEMBLY, RS-25 (E2045) | - | R130701A4 | 97M62040-001 | 97M62040-001 | ENGINE ASSEMBLY, RS-25 (E2045) | C | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Drawing | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
General Notes Number: R130701A4_JTM | - | R130701A4_JTM.ASM Notes.pdf | 97M62040-001 | 97M62040-001 | General Notes Number: R130701A4_JTM | 3 | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Drawing | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
ENGINE ASSEMBLY, RS-25 (E2056, E2058) | - | R130701A1 | 97M62040-001 | 97M62040-001 | ENGINE ASSEMBLY, RS-25 (E2056, E2058) | D | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Drawing | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
General Notes Number: R130701A1_JTM | - | R130701A1_JTM.ASM Notes.pdf | 97M62040-001 | 97M62040-001 | General Notes Number: R130701A1_JTM | 4 | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Drawing | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
ENGINE ASSEMBLY, RS-25 (E2060) | - | R130701A5 | 97M62040-001 | 97M62040-001 | ENGINE ASSEMBLY, RS-25 (E2060) | C | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Drawing | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
ENGINE ASSEMBLY, RS-25 (E2060) - Notes | - | R130701A5_JTM.ASM Notes.pdf | 97M62040-001 | 97M62040-001 | General Notes Number: R130701A5_JTM | 3 | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Drawing | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
RS-25 Engine Control Unit (ECU) Operational Flight Program Software Requirements Specification | - | RCP300012 | 97M62040-001 | 97M62040-001 | RS-25 Engine Control Unit (ECU) Operational Flight Program Software Requirements Specification | E | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Spec | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
RS-25 Engine Control Unit Advanced Health Management Software Requirements Specification | - | RCP300013 | 97M62040-001 | 97M62040-001 | RS-25 Engine Control Unit Advanced Health Management Software Requirements Specification | E | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Spec | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
SCPR 395 – RCP300013 FROM-TO Changes | - | ECP RS25-0038 / CA-021723 | 97M62040-001 | 97M62040-001 | SCPR 395 – RCP300013 FROM-TO Changes | New | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Spec | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
INSTRUMENTATION PROGRAM AND COMMAND LIST (IPCL) SPECIFICATION | - | RD12-247 | 97M62040-001 | 97M62040-001 | INSTRUMENTATION PROGRAM AND COMMAND LIST (IPCL) SPECIFICATION | E | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Spec | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Instrumentation Program Command List, Appendix | - | RD12-247_Rev_E_Appendix_B_20161122 | 97M62040-001 | 97M62040-001 | Instrumentation Program Command List, Appendix | New | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Spec | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
STANDARD REPAIR PROCEDURE FOR SSME LIQUID AIR INSULATOR BOOT COVERS | - | RF0001-345 | 97M62040-001 | 97M62040-001 | STANDARD REPAIR PROCEDURE FOR SSME LIQUID AIR INSULATOR BOOT COVERS | New | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Spec | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-03 07:57 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
RS-25 Closeout Photo Requirements | - | TPD-340002 | 97M62040-001 | 97M62040-001 | RS-25 Closeout Photo Requirements | New | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Spec | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:30 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
RS-25 Engine Control Unit Software Operational Notes | - | TPD-339793 | 97M62040-001 | 97M62040-001 | RS-25 Engine Control Unit Software Operational Notes Document | New | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Spec | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:30 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
CONNECTOR TORQUE LOCK COMPOUND, APPLICATION OF | - | RA1606-018 | 97M62040-001 | 97M62040-001 | CONNECTOR TORQUE LOCK COMPOUND, APPLICATION OF | D | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Spec | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:30 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
RS-25 ENGINE DRYING PROCEDURE | - | RL00663 | 97M62040-001 | 97M62040-001 | RS-25 ENGINE DRYING PROCEDURE | T | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Spec | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:30 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Installation of Bolts, Nuts, Screws, and Studs | - | RA0101-002 | 97M62040-001 | 97M62040-001 | Installation of Bolts, Nuts, Screws, and Studs | AJ | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Spec | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:30 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
SILICONE PRIMER FOR CRYOGENIC BONDING APPLICATIONS | - | RB0120-036 | 97M62040-001 | 97M62040-001 | SILICONE PRIMER FOR CRYOGENIC BONDING APPLICATIONS | F | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Spec | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:30 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
SILICONE ELASTOMER, FILLED, ROOM TEMPERATURE VULCANIZING | - | RB0120-005 | 97M62040-001 | 97M62040-001 | SILICONE ELASTOMER, FILLED, ROOM TEMPERATURE VULCANIZING | V | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Spec | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:30 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
ENGINE FLUID SYSTEMS SCHEMATIC | - | TPD-330581 | 97M62040-001 | 97M62040-001 | ENGINE FLUID SYSTEMS SCHEMATIC | New | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Drawing | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-05-16 16:30 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
ISPE Cable Interconnect Diagram |  | 97M43300 |  |  | ISPE Cable Interconnect Diagram | A | Link to Product | GSDO-C1048-X | Approved | Approved | GSDO-D1048-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | SLS/SPIE Request | SLS/SPIE | Integrated Test | Baselined |  | Schematic | NVR |  |  | 2018-06-22 11:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:15 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/07/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
ISPE Electrical System Schematic Diagram |  | 97M43301 |  |  | ISPE Electrical System Schematic Diagram | - | Link to Product | GSDO-C1048-X | Approved | Approved | GSDO-D1048-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | SLS/SPIE Request | SLS/SPIE | Integrated Test | Baselined |  | Schematic | NVR |  |  | 2018-06-22 11:33 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:15 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/07/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
ISPE Grounding Diagram |  | 97M43302 |  |  | ISPE Grounding Diagram | - | Link to Product | GSDO-C1048-X | Approved | Approved | GSDO-D1048-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | SLS/SPIE Request | SLS/SPIE | Integrated Test | Baselined |  | Schematic | NVR |  |  | 2018-06-22 11:35 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:15 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/07/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Battery Installation, CBC/DCSS, Launch Site |  | 1G25675 | 1G50001 | 1G5000 | Battery Installation, CBC/DCSS, Launch Site | H | Link to Product | GSDO-C1048-X | Approved | Approved | GSDO-D1048-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Update | SLS/SPIE Request | SLS/SPIE | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined |  | Drawing | VR |  |  | 2018-06-22 11:41 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:15 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/07/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Electrical Equipment Installation, Launch Site |  | 1G25676 | 1G50001 | 1G5000 | Electrical Equipment Installation, Launch Site | D | LINK TO PRODUCT | GSDO-C1048-X | Approved | Approved | GSDO-D1048-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Superceded | SLS/SPIE Request | SLS/SPIE | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined | ​This item was Superceded/Deleted without a successor replacement on GSDO-D1140-X in December 2018. | Drawing | VR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2018-06-22 11:56 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-12-06 08:56 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/07/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Installation, Pre-VAB |  | 1G50009 | 1G50001 | 1G5000 | Installation, Pre-VAB | B | LINK TO PRODUCT | GSDO-C1048-X | Approved | Approved | GSDO-D1048-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Update | SLS/SPIE Request | SLS/SPIE | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined |  | Drawing | VR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2018-06-22 12:04 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:15 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/07/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Blanket Instl, Hydrazine Bottle, Launch Site - ICPS |  | 1G50144 | 1G50001 | 1G50000 | Blanket Instl, Hydrazine Bottle, Launch Site - ICPS | B | LINK TO PRODUCT | GSDO-C1048-X | Approved | Approved | GSDO-D1048-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Update | SLS/SPIE Request | SLS/SPIE | VAB Rollout for WDR | Baselined |  | Drawing | VR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2018-06-22 12:09 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:15 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/07/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Blanket Instl, Equipment Shelf, Launch Site - ICPS |  | 1G50145 | 1G50001 | 1G50000 | Blanket Instl, Equipment Shelf, Launch Site - ICPS | C | LINK TO PRODUCT | GSDO-C1048-X | Approved | Approved | GSDO-D1048-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Update | SLS/SPIE Request | SLS/SPIE | VAB Rollout for WDR | Baselined |  | Drawing | VR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2018-06-22 12:14 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:15 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/07/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Door Access Kit – LVSA |  | 38610445 | 97M62215-001 | 1G50000 | Door Access Kit – LVSA | C | LINK TO PRODUCT | GSDO-C1048-X | Approved | Approved | GSDO-D1048-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Superceded | SLS/SPIE Request | SLS/SPIE | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined | ​This item was superceded by [38610530, (Kit, Flight Ship Loose Items - LVSA) Rev A] upon approval of GSDO-D1140-X in December 2018. | Drawing | VR | CI-1.b - Launch Vehicle Stage Adapter (LVSA) |  | 2018-06-22 12:17 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-12-06 08:51 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/07/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Design Standard Requirements for Critical Design Characteristics |  | 0-70924 | 1G50001 | 1G50000 | Design Standard Requirements for Critical Design Characteristics | D | LINK TO PRODUCT | GSDO-C1048-X | Approved | Approved | GSDO-D1048-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Update | SLS/SPIE Request | SLS/SPIE | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined |  | Drawing | NVR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2018-06-22 12:22 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:15 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/07/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
BOLTS, SCREWS, NUTS, AND WASHERS, INSTALLATION AND INSPECTION OF |  | STP1023 | 1G50001 | 1G50000 | BOLTS, SCREWS, NUTS, AND WASHERS, INSTALLATION AND INSPECTION OF | B | LINK TO PRODUCT | GSDO-C1048-X | Approved | Approved | GSDO-D1048-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | SLS/SPIE Request | SLS/SPIE | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined | ​replaces the Superseded STP0381 on CR GSDO-C1048-X | Spec | NVR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2018-06-22 12:30 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-11-01 09:24 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/07/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Update LSAIB to Add Booster Drawing STW7-18350, Revision F |  | GSDO-IDM-037 |  |  | STW78-18370, Process Standard for Electrical Harness Installation | F | GSDO-IDM-037 |  | Coordination |  | GSDO-IDM-037 | Jones, John T. | ITAR | IDM | Add | Booster Request | SLS/Booster |  | Baselined |  | Drawing | VR |  |  | 2018-06-28 13:26 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-31 15:17 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] |  | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Process Standard for Electrical Harness Installation |  | STW7-18350 | 97M62060-001 | 97M62040-001 | Process Standard for Electrical Harness Installation | F | Link to product |  | Approved |  | GSDO-IDM-037 | Jones, John T. |  | IDM | Add | Booster Request | SLS/Booster | Aft Booster Assembly Buildup | Baselined |  | Drawing | VR |  |  | 2018-07-10 12:47 | Cannon, Dayna (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-11-01 09:24 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] |  | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
ENGINE CONTROLLER, RS-25, PRESSURIZATION PROCEDURE | - | RL02135_Rev_A | 97M62040-001 | 97M62040-001 | ENGINE CONTROLLER, RS-25, PRESSURIZATION PROCEDURE | A | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Spec | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-08-14 11:53 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-11-01 09:24 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Diagram, Electrical Interconnect – RS-25 - Notes | - | 3R130707D1.DRW Notes | 97M62040-001 | 97M62040-001 | Diagram, Electrical Interconnect – RS-25 - Notes | 4 | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Drawing | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-08-14 11:57 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Diagram, Electrical Interconnect - RS-25 | - | 3R130707D1 | 97M62040-001 | 97M62040-001 | Diagram, Electrical Interconnect – RS-25 | C | Link to Product | GSDO-C1050-X | Approved | Approved | GSDO-D1050-X | Robertson, Doug | SBU;#ITAR;#Limited Rights Data | CR | Add | Engines - CSE/RS-25 | SLS/Engines | Integrated Test | Baselined |  | Drawing | NVR | CI-1D - Launch Vehicle Assembly |  | 2018-08-14 12:05 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-08-29 12:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 08/28/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
ACCESS DOOR INSTL |  | PL201-010102 | 97M62050-001 | 97M62040-001 | ACCESS DOOR INSTL | A | Link to Product | GSDO-C1092-X | Approved | Approved | GSDO-D1092-X | Rubio, Rommel | ITAR | CR | Add | Core Stage Request | SLS/Core Stage | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined |  | Drawing | VR | CI-1.a - Integrated Core Contractor Assembly |  | 2018-09-04 14:19 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-10 11:13 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 10/09/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
ACCESS DOOR INSTL |  | 201-010102 | 97M62050-001 | 97M62040-001 | ACCESS DOOR INSTL | A | Link to Product | GSDO-C1092-X | Approved | Approved | GSDO-D1092-X | Rubio, Rommel | ITAR | CR | Add | Core Stage Request | SLS/Core Stage | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined |  | Drawing | VR | CI-1.a - Integrated Core Contractor Assembly |  | 2018-09-04 14:23 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-10 11:13 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 10/09/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
PYRO INSTL, SYSTEMS TUNNEL |  | PL201-010182 | 97M62050-001 | 97M62040-001 | PYRO INSTL, SYSTEMS TUNNEL | C | Link to Product | GSDO-C1092-X | Approved | Approved | GSDO-D1092-X | Rubio, Rommel | ITAR | CR | Add | Core Stage Request | SLS/Core Stage | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined |  | Drawing | VR | CI-1.a - Integrated Core Contractor Assembly |  | 2018-09-04 14:26 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-10 11:13 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 10/09/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
PYRO INSTL, SYSTEMS TUNNEL |  | 201-010182 | 97M62050-001 | 97M62040-001 | PYRO INSTL, SYSTEMS TUNNEL | A | Link to Product | GSDO-C1092-X | Approved | Approved | GSDO-D1092-X | Rubio, Rommel | ITAR | CR | Add | Core Stage Request | SLS/Core Stage | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined |  | Drawing | VR | CI-1.a - Integrated Core Contractor Assembly |  | 2018-09-04 14:28 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-10 11:13 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 10/09/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
ORDNANCE INSTL, SYSTEMS TUNNEL |  | PL201-010184 | 97M62050-001 | 97M62040-001 | ORDNANCE INSTL, SYSTEMS TUNNEL | C | Link to Product | GSDO-C1092-X | Approved | Approved | GSDO-D1092-X | Rubio, Rommel | ITAR | CR | Add | Core Stage Request | SLS/Core Stage | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined |  | Drawing | VR | CI-1.a - Integrated Core Contractor Assembly |  | 2018-09-04 14:29 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-10 11:13 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 10/09/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
ORDNANCE INSTL, SYSTEMS TUNNEL |  | 201-010184 | 97M62050-001 | 97M62040-001 | ORDNANCE INSTL, SYSTEMS TUNNEL | A | Link to Product | GSDO-C1092-X | Approved | Approved | GSDO-D1092-X | Rubio, Rommel | ITAR | CR | Add | Core Stage Request | SLS/Core Stage | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined |  | Drawing | VR | CI-1.a - Integrated Core Contractor Assembly |  | 2018-09-04 14:31 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-10 11:13 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 10/09/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
MANIFOLD INSTL, PYRO, SYSTEMS TUNNEL |  | PL201-010185 | 97M62050-001 | 97M62040-001 | MANIFOLD INSTL, PYRO, SYSTEMS TUNNEL | A | Link to Product | GSDO-C1092-X | Approved | Approved | GSDO-D1092-X | Rubio, Rommel | ITAR | CR | Add | Core Stage Request | SLS/Core Stage | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined |  | Drawing | VR | CI-1.a - Integrated Core Contractor Assembly |  | 2018-09-04 14:33 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-10 11:13 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 10/09/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
MANIFOLD INSTL, PYRO, SYSTEMS TUNNEL |  | 201-010185 | 97M62050-001 | 97M62040-001 | MANIFOLD INSTL, PYRO, SYSTEMS TUNNEL | A | Link to Product | GSDO-C1092-X | Approved | Approved | GSDO-D1092-X | Rubio, Rommel | ITAR | CR | Add | Core Stage Request | SLS/Core Stage | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined |  | Drawing | VR | CI-1.a - Integrated Core Contractor Assembly |  | 2018-09-04 14:35 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-10 11:13 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 10/09/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
PYRO INSTL, INTERTANK |  | PL201-014060 | 97M62050-001 | 97M62040-001 | PYRO INSTL, INTERTANK | B | Link to Product | GSDO-C1092-X | Approved | Approved | GSDO-D1092-X | Rubio, Rommel | ITAR | CR | Add | Core Stage Request | SLS/Core Stage | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined |  | Drawing | VR | CI-1.a - Integrated Core Contractor Assembly |  | 2018-09-04 14:37 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-10 11:13 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 10/09/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
PYRO INSTL, INTERTANK |  | 201-014060 | 97M62050-001 | 97M62040-001 | PYRO INSTL, INTERTANK | B | Link to Product | GSDO-C1092-X | Approved | Approved | GSDO-D1092-X | Rubio, Rommel | ITAR | CR | Add | Core Stage Request | SLS/Core Stage | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined |  | Drawing | VR | CI-1.a - Integrated Core Contractor Assembly |  | 2018-09-04 14:38 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-10 11:13 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 10/09/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
COVER INSTALLATION, VEHICLE STABILIZER |  | PL201-015160 | 97M62050-001 | 97M62040-001 | COVER INSTALLATION, VEHICLE STABILIZER | A | Link to Product | GSDO-C1092-X | Approved | Approved | GSDO-D1092-X | Rubio, Rommel | ITAR | CR | Add | Core Stage Request | SLS/Core Stage | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined |  | Drawing | VR | CI-1.a - Integrated Core Contractor Assembly |  | 2018-09-04 14:40 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-10 11:13 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 10/09/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
COVER INSTALLATION, VEHICLE STABILIZER |  | 201-015160 | 97M62050-001 | 97M62040-001 | COVER INSTALLATION, VEHICLE STABILIZER | A | Link to Product | GSDO-C1092-X | Approved | Approved | GSDO-D1092-X | Rubio, Rommel | ITAR | CR | Add | Core Stage Request | SLS/Core Stage | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined |  | Drawing | VR | CI-1.a - Integrated Core Contractor Assembly |  | 2018-09-04 14:41 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-10 11:13 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 10/09/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
ICPS RL10 Throat Plug Removal, Inspection and Installation | 9-25-18 | GSDO-CHIT-0001 | 97M62105-001 | 97M62105-001 | ICPS RL10 Throat Plug Removal, Inspection and Installation | - | Link to Product | GSDO-C1099-X | Approved | Approved | GSDO-D1099-X | Bengoa, Alex | SBU;#Limited Rights Data | CR | Add | SLS/SPIE Request | SLS/SPIE |  | Baselined |  | Chit | VR | CI-1.d - Interim Cryogenic Propulsion Stage (ICPS) | 15 - ICPS Flight Stage - 1G50001-1 - Flight | 2018-09-17 10:18 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-10-09 09:19 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 09/25/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
LVSA Integrated Assembly |  | 18610001 | 97M62215-001 | 97M62040-001 | LVSA Integrated Assembly | A | Link to Product | GSDO-C1140-X | Approved | Approved | GSDO-D1140-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Update | LVSA Request | SLS/SPIE | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined |  | Drawing | VR | CI-1.b - Launch Vehicle Stage Adapter (LVSA) | 47 - Launch Vehicle Stage Adapter (LVSA) - - Flight | 2018-11-02 11:44 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-12-06 08:43 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 12/04/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Door, Access Installation, Flight LVSA |  | 18610026 | 97M62215-001 | 97M62040-001 | Door, Access Installation, Flight LVSA | - | Link to Product | GSDO-C1140-X | Approved | Approved | GSDO-D1140-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | LVSA Request | SLS/SPIE | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined | ​Replaces/Supercedes [18610016, (Door, Access Installation, Flight LVSA) rev A] on GSDO-C1140-X. | Drawing | VR | CI-1.b - Launch Vehicle Stage Adapter (LVSA) | 47 - Launch Vehicle Stage Adapter (LVSA) - - Flight | 2018-11-02 11:58 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-12-06 08:45 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 12/04/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Kit, Flight Ship Loose Items - LVSA |  | 38610530 | 97M62215-001 | 97M62040-001 | Kit, Flight Ship Loose Items - LVSA | A | Link to Product | GSDO-C1140-X | Approved | Approved | GSDO-D1140-X | Bengoa, Alex | ITAR;#Limited Rights Data | CR | Add | LVSA Request | SLS/SPIE | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | Baselined | ​Replaces/Supercedes [38610445, (Door Access Kit - LVSA) Rev C] on GSDO-C1140-X. | Drawing | NVR | CI-1.b - Launch Vehicle Stage Adapter (LVSA) | 47 - Launch Vehicle Stage Adapter (LVSA) - - Flight | 2018-11-02 12:02 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-12-06 08:53 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 12/04/2018 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
Standard for Booster Configuration, Space Launch System |  | STW9-19166 | 97M62060-001 | 97M62040-001 | Standard for Booster Configuration, Space Launch System | C | Link to Specification |  | Coordination |  | GSDO-D1157-X | Jones, John T. | SBU;#ITAR | S2D | Update | Booster Request | SLS/Booster | Aft Booster Assembly Buildup | In Work | ​This Specification supersedes STW9-19166 Rev B and also supersedes GSDO-IDM-037 which cancels STW7-18350 Rev F. | Spec | VR | CI-1E - Solid Rocket Booster (SRB) |  | 2018-11-29 08:46 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-11-29 08:55 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] |  | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
HYDRAULIC SERVICE PANEL ASSY |  | PL201-011760 | 97M62050-001 | 97M62040-001 | HYDRAULIC SERVICE PANEL ASSY | C | Link to Product | GSDO-C1160-X |  | In Work |  | Rubio, Rommel | ITAR | CR | Add | Core Stage Request | SLS/Core Stage | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | In Work |  | Drawing | VR | CI-1.a - Integrated Core Contractor Assembly |  | 2018-12-03 14:14 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-12-03 14:24 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 01/15/2019 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
HYDRAULIC SERVICE PANEL ASSY |  | 201-011760 | 97M62050-001 | 97M62040-001 | HYDRAULIC SERVICE PANEL ASSY | C | Link to Product | GSDO-C1160-X |  | In Work |  | Rubio, Rommel | ITAR | CR | Add | Core Stage Request | SLS/Core Stage | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | In Work |  | Drawing | VR | CI-1.a - Integrated Core Contractor Assembly |  | 2018-12-03 14:16 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-12-03 14:25 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 01/15/2019 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
GROUND STRAP INSTL KIT, CORE - BOOSTER |  | PL201-019014 | 97M62050-001 | 97M62040-001 | GROUND STRAP INSTL KIT, CORE - BOOSTER | A | Link to Product | GSDO-C1160-X |  | In Work |  | Rubio, Rommel | ITAR | CR | Add | Core Stage Request | SLS/Core Stage | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | In Work |  | Drawing | VR | CI-1.a - Integrated Core Contractor Assembly |  | 2018-12-03 14:20 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-12-03 14:25 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 01/15/2019 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
GROUND STRAP INSTL KIT, CORE - BOOSTER |  | 201-019014 | 97M62050-001 | 97M62040-001 | GROUND STRAP INSTL KIT, CORE - BOOSTER | A | Link to Product | GSDO-C1160-X |  | In Work |  | Rubio, Rommel | ITAR | CR | Add | Core Stage Request | SLS/Core Stage | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | In Work |  | Drawing | VR | CI-1.a - Integrated Core Contractor Assembly |  | 2018-12-03 14:21 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-12-03 14:25 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 01/15/2019 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
JOIN HARDWARE INSTL KIT, CORE - LVSA |  | PL201-019015 | 97M62050-001 | 97M62040-001 | JOIN HARDWARE INSTL KIT, CORE - LVSA | - | Link to Product | GSDO-C1160-X |  | In Work |  | Rubio, Rommel | ITAR | CR | Add | Core Stage Request | SLS/Core Stage | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | In Work |  | Drawing | VR | CI-1.a - Integrated Core Contractor Assembly |  | 2018-12-03 14:23 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-12-03 14:25 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 01/15/2019 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline
JOIN HARDWARE INSTL KIT, CORE - LVSA |  | 201-019015 | 97M62050-001 | 97M62040-001 | JOIN HARDWARE INSTL KIT, CORE - LVSA | - | Link to Product | GSDO-C1160-X |  | In Work |  | Rubio, Rommel | ITAR | CR | Add | Core Stage Request | SLS/Core Stage | Core Stage/ICPS/Launch Vehicle Stage Adapter Mate | In Work |  | Drawing | VR | CI-1.a - Integrated Core Contractor Assembly |  | 2018-12-03 14:23 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 2018-12-03 14:25 | Herrman, Dwight E. (KSC-KLXSII)[Millennium Engineering and Integration Company] | 01/15/2019 | Item | GSDO-ICM-Tools/CMW/Lists/EM1Baseline